## Bug Reports
Bug ID | Date Filed | Severity | Component | Title | Steps to Reproduce | Expected Behavior | Actual Behavior | Affected Users | Platform | Status | Sprint
BUG-1187 | 2025-06-10 | P1 | Navigation | Back stack corrupted after deep link from notification | 1. Receive push notification 2. Tap notification 3. View content 4. Press back button | Should return to previous app/home screen | Returns to random app screen or loops between two screens. Back stack appears corrupted when app is launched via deep link. | ~12,000/month | Both | Open | Sprint 47
BUG-1182 | 2025-06-08 | P1 | Search | Search index missing 40% of app content | 1. Open search 2. Type "letters" 3. View results | Should show VA Letters feature | No results. Search index only covers Health and Claims sections. Benefits, Profile, Letters, and Payment sections are not indexed. | All search users | Both | Confirmed | Sprint 47
BUG-1175 | 2025-06-05 | P2 | Navigation | Tab bar disappears after rotating device | 1. Open app in portrait 2. Rotate to landscape 3. Rotate back to portrait | Tab bar should persist | Bottom tab bar vanishes. Only recoverable by force-closing and reopening app. | ~3,200/month | iOS | In Progress | Sprint 46
BUG-1171 | 2025-06-03 | P1 | Accessibility | TalkBack reads nav items in wrong order | 1. Enable TalkBack 2. Navigate to home screen 3. Swipe right through elements | Should read top-to-bottom, left-to-right in logical order | TalkBack reads: footer links, then body content, then header, then nav. DOM order does not match visual layout. | All TalkBack users | Android | Open | Sprint 47
BUG-1168 | 2025-06-02 | P2 | Task Completion | Form state lost on app backgrounding (iOS) | 1. Start any multi-step form 2. Switch to another app briefly 3. Return to VA app | Form should preserve entered data | All form fields reset to empty. Affects appointment scheduling, secure messages, and document upload flows. State is not persisted to disk. | ~8,500/month | iOS | Confirmed | Sprint 48
BUG-1163 | 2025-05-30 | P3 | Navigation | Breadcrumb trail truncates to "..." on smaller screens | 1. Navigate 3+ levels deep on a phone with <6" screen 2. Observe breadcrumb | Breadcrumbs should be scrollable or show at least current + parent | Breadcrumb shows "... > Current Page" losing all intermediate context. Users cannot navigate back to mid-level pages. | ~5,100/month | Both | Open | Backlog
BUG-1159 | 2025-05-28 | P2 | Search | Search results flicker and reorder while loading | 1. Type a query 2. Watch results appear | Results should load once in stable order | Results appear, disappear, reappear in different order over 2-3 seconds. Causes users to tap wrong items. Likely race condition in async result merging. | ~6,800/month | Both | Confirmed | Sprint 47
BUG-1154 | 2025-05-26 | P1 | Accessibility | Focus trap in appointment date picker | 1. Enable any screen reader 2. Navigate to appointment scheduling 3. Open date picker 4. Try to dismiss | Should be able to close date picker and continue | Keyboard/switch focus gets trapped inside date picker component. No escape mechanism. User must force-close app. | All assistive tech users | Both | Escalated | Sprint 46
BUG-1149 | 2025-05-24 | P3 | Navigation | Health category shows 0 items badge incorrectly | 1. Open app with no new health notifications 2. Check Health tab icon | No badge should appear if count is 0 | Red badge with "0" displays on Health tab. Confuses users into thinking they have notifications. Badge logic shows count even when zero. | ~15,000/month | Android | Open | Sprint 48
BUG-1144 | 2025-05-22 | P2 | Task Completion | File upload silently fails for files > 5MB | 1. Go to claim evidence upload 2. Select a PDF > 5MB 3. Tap upload | Should show error with file size limit | Upload button shows spinner for 30 seconds then returns to upload screen with no error message. File is not uploaded. No size limit documented in UI. | ~2,100/month | Both | In Progress | Sprint 47
BUG-1139 | 2025-05-20 | P2 | Navigation | Hamburger menu overlay blocks screen reader dismiss gesture | 1. Open hamburger menu with VoiceOver active 2. Try to dismiss with two-finger scrub gesture | Menu should close on accessibility dismiss gesture | Gesture is not recognized. VoiceOver users must find and tap a small X button to close menu, which is not announced as "close". | All VoiceOver users | iOS | Open | Sprint 48
BUG-1133 | 2025-05-18 | P3 | Search | Recent searches not persisting between sessions | 1. Search for something 2. Close app completely 3. Reopen and tap search | Recent searches should appear | Recent search list is empty. Only persists during single session. localStorage is cleared on app termination. | All search users | Both | Open | Backlog

## Feature Requests
Request ID | Date | Source | Category | Title | Description | User Impact Statement | Votes/Mentions | Priority Score | Status | Linked Bugs
FR-301 | 2025-06-11 | App Store Review | Navigation | Quick Actions / Shortcuts from Home Screen | Add a customizable quick-action panel on the home screen so veterans can pin their 3-5 most-used features (Rx Refill, Check Claims, Appointments, Secure Message). Similar to iOS widget functionality. | "I use this app for exactly 2 things - refilling meds and checking my claim. Both take 4+ taps to reach." | 847 | 92 | Under Review
FR-298 | 2025-06-09 | Help Desk Pattern | Search | Implement Fuzzy Search with Autocomplete | Current search is exact-match only. Need fuzzy matching, spell correction, autocomplete suggestions, and synonym support (e.g., "meds" = "medications" = "prescriptions"). | "I can never find anything with search. I have to know the exact word VA uses for everything." | 612 | 88 | Approved | BUG-1182, BUG-1133
FR-295 | 2025-06-07 | Veteran Focus Group | Accessibility | Full Screen Reader Navigation Audit & Remediation | Comprehensive audit and fix of all screen reader navigation paths. Ensure logical reading order, proper ARIA labels, focus management on route changes, and accessible custom components. | "I'm a blind veteran and this app is almost unusable with VoiceOver. I end up calling the 800 number instead." | 234 | 95 | Approved | BUG-1171, BUG-1154, BUG-1139
FR-291 | 2025-06-05 | App Store Review | Navigation | Unified Information Architecture | Restructure the Health/Benefits split into task-based navigation. Veterans don't think in VA organizational terms. Group by what they want to DO: "Manage My Care", "Track My Benefits", "My Documents". | "Why do I need to know if something is Health or Benefits? I just need to find my stuff." | 1203 | 90 | Under Review | HD-4502
FR-287 | 2025-06-03 | Contact Center Data | Task Completion | Auto-Save for All Forms and Drafts | Implement persistent auto-save across all form inputs, message drafts, and multi-step flows. Save state should survive app backgrounding, device rotation, and session timeout. | "I spent 20 minutes writing a message to my doctor and it just vanished when I checked my calendar." | 531 | 85 | Under Review | BUG-1168
FR-283 | 2025-06-01 | Veteran Advisory Committee | Navigation | Contextual Notification Deep Linking | Push notifications should deep link directly to relevant content. Message notifications open Messages, appointment reminders open that appointment, claim updates open that claim. | "What's the point of notifications if I still have to dig through the app to find what it's about?" | 389 | 78 | Backlog | BUG-1187
FR-279 | 2025-05-29 | Accessibility Audit | Accessibility | Dynamic Type / System Font Size Support | Respect system-level font size preferences across ALL UI elements including navigation, headers, buttons, and badges. Currently only body text scales. | "I set my phone to large text for a reason. Half this app ignores that setting." | 445 | 82 | Approved | BUG-1163
FR-275 | 2025-05-27 | App Store Review | Search | Full-Text Search Across Messages and Documents | Extend search to index secure message content, uploaded documents (OCR), appointment notes, and letter content. Currently only searches page titles. | "I know my doctor mentioned a medication name in a message last month but I can't search for it." | 298 | 72 | Backlog | BUG-1182
FR-271 | 2025-05-25 | Usability Study | Navigation | Persistent Breadcrumb with Full Path | Show full navigation breadcrumb that is horizontally scrollable on smaller screens. Include tap targets for each level to allow mid-path navigation. | "I get lost 3 levels deep and have no idea how to get back to where I was without starting over." | 187 | 65 | Backlog | BUG-1163
FR-267 | 2025-05-23 | Help Desk Pattern | Task Completion | Smart Prescription List with Filters | Add filters (Active/Expired/Refillable), sort options (name/date/status), and a "Refill All Eligible" batch action to the prescriptions list. | "I have 14 prescriptions showing and half are from years ago. Just show me what I can actually refill." | 756 | 80 | Under Review | HD-4425